## Slide 1
Guidance on audit of the use and development of key national indicators
Anton Kosyanenko, Accounts Chamber of the Russian Federation
Bratislava, Slovakia, April 1-4, 2019

## Slide 2
PRESENTATION PLAN
2
Project report and current status
Key points of the Exposure draft
Steps to be taken

## Slide 3
PROJECT TIMELINE
 | 2017 |  |  | 2018 |  |  |  |  |  |  |  |  |  |  |  | 2019 |  |  |  |  |  |  |  | 
 | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
PP adjustment to FIPP requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Approval of the PP by KSC and FIPP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Exposure draft development Agreement with WG on KNI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FiPP approval of the Exposure draft |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Agreement with PAS, CAS, WG on Programme Evaluation, Expert Group on SDGs, WG on Big Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FiPP approval of the Exposure draft |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Exposure period FIPP approval of the Exposure draft |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Endorsement version |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FIPP approval of the Endorsement version |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final Pronouncement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
March 27-29, 2018
11th meeting of the INTOSAI WG on KNI
August 20-24, 2018,
FIPP meeting
(ED needs to be revised)
July 30, 2018
Preliminary draft was disseminated among WG members
November 26-30, 2018,
Exposure draft approval
at FIPP meeting
December 27, 2018,
Start of the exposure
period
September 2019,
XXIII INCOSAI
April 1-4, 2019
12th meeting of the INTOSAI WG on KNI
June 25-28, 2019
FIPP meeting
3

## Slide 4
Comments were received from 5 members of the WG on KNI:
AFROSAI-E
SAI of Austria
SAI of Bulgaria
SAI of Pakistan
SAI of Slovakia
EXPOSURE DRAFT DEVELOPMENT
4

## Slide 5
PROJECT TIMELINE
 | 2017 |  |  | 2018 |  |  |  |  |  |  |  |  |  |  |  | 2019 |  |  |  |  |  |  |  | 
 | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
PP adjustment to FIPP requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Approval of the PP by KSC and FIPP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Exposure draft development Agreement with WG on KNI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FiPP approval of the Exposure draft |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Agreement with PAS, CAS, WG on Programme Evaluation, Expert Group on SDGs, WG on Big Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FiPP approval of the Exposure draft |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Exposure period FIPP approval of the Exposure draft |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Endorsement version |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FIPP approval of the Endorsement version |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final Pronouncement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
March 27-29, 2018
11th meeting of the INTOSAI WG on KNI
August 20-24, 2018,
FIPP meeting
(ED needs to be revised)
July 30, 2018
Preliminary draft was disseminated among WG members
November 26-30, 2018,
Exposure draft approval
at FIPP meeting
December 27, 2018,
Start of the exposure
period
September 2019,
XXIII INCOSAI
April 1-4, 2019
12th meeting of the INTOSAI WG on KNI
June 25-28, 2019
FIPP meeting
3

## Slide 6
EXPOSURE DRAFT DEVELOPMENT
FIPP
12 comments
12 accepted
Compliance Audit Subcommittee
3 comments
3 accepted
Performance Audit Subcommittee
25 comments
8 accepted
11 not accepted
6 comment provided
INTOSAI Working group on Programme Evaluation
66 comments
50 accepted
16 not accepted
5
Major changes :
GUID is transferred to the ISSAI 5000-series
GUID is repositioned in order to allow for its application in performance and compliance audits as well as programmes evaluations with necessary references to relevant standards (ISSAI 300, ISSAI 400, ISSAI 3000 and ISSAI 4000, ISSAI 3100 and ISSAI 3200, INTOSAI GOV 9400)
The structure of GUID was rearranged in order to fully comply with the FIPP drafting conventions

## Slide 7
PROJECT TIMELINE
 | 2017 |  |  | 2018 |  |  |  |  |  |  |  |  |  |  |  | 2019 |  |  |  |  |  |  |  | 
 | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
PP adjustment to FIPP requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Approval of the PP by KSC and FIPP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Exposure draft development Agreement with WG on KNI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FiPP approval of the Exposure draft |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Agreement with PAS, CAS, WG on Programme Evaluation, Expert Group on SDGs, WG on Big Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FiPP approval of the Exposure draft |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Exposure period FIPP approval of the Exposure draft |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Endorsement version |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FIPP approval of the Endorsement version |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final Pronouncement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
March 27-29, 2018
11th meeting of the INTOSAI WG on KNI
August 20-24, 2018,
FIPP meeting
(ED needs to be revised)
July 30, 2018
Preliminary draft was disseminated among WG members
November 26-30, 2018,
Exposure draft approval
at FIPP meeting
December 27, 2018,
Start of the exposure
period
September 2019,
XXIII INCOSAI
April 1-4, 2019
12th meeting of the INTOSAI WG on KNI
June 25-28, 2019
FIPP meeting
3

## Slide 8
EXPOSURE DRAFT DEVELOPMENT
Exposure period ended on March 27,2019
13 INTOSAI members:
SAI of Australia
SAI of Austria
SAI of Canada
SAI of Czech Republic
SAI of Ecuador
SAI of Finland
SAI of Kuwait
SAI of Lithuania
SAI of Malta
SAI of Mexico
SAI of Philippines
SAI of South Africa
SAI of Sudan
2 organizations:
Institute of Internal Auditors
The International Consortium on Governmental Financial Management
6

## Slide 9
PRESENTATION PLAN
Project timeline
Key points of the Exposure draft
Steps to be taken
7

## Slide 10
Structure of the GUID
Introduction
Definition of KNI
Objective
Scope
Central concepts for the audit of use and development of KNI
supplementary guidance provided for Independence and ethics, Intended users and responsible parties, Subject matter, Audit objective(s), Audit approach, Audit criteria, Skills
Criteria structure for the audit of use and development of KNI
including 6 categories of audit questions structured in maturity models and a section on evaluation of goals attainment
7

## Slide 11
ISSAI 1
The Lima
Declaration
ISSAI 10 Mexico Declaration
on SAI Independence
ISSAI 100 Fundamental Principles of Public-Sector Auditing
ISSAI 300 Fundamental Principles of Performance Auditing
ISSAI 3000 Standard for Performance Auditing
ISSAI 5130 Sustainable Development:
The Role of Supreme Audit Institutions
INTOSAI GOV 9400 Guidelines on the Evaluation of Public Policies
Auditing Preparedness for Implementation of Sustainable Development Goals
Place of the GUID within ISSAI Framework
ISSAI 400 Fundamental Principles of Compliance Auditing
ISSAI 4000 Compliance Audit Guidelines
8
Fundamental principles
May be a part of
May provide additional
guidance for

## Slide 12
For the purpose of the GUID KNI would be defined as a set of indicators used by the government in order to set objectives, monitor progress and evaluate goals attainment as well as to measure the performance of the government activities, programmes, policies, operations or undertakings, as well as the direct and indirect impacts of public policies and programmes.
9
Definition of KNI

## Slide 13
The five roles SAIs may take in the use and development of KNI
identification of the need for KNI within the country
contribution to selected education and promotion efforts in connection with KNI
assessment of the process used to develop the indicators and/or systems
audit of the quality, validity, and reliability of the indicator information
use of indicators to assess and report on national progress
9
The GUID is non-mandatory guidance that is intended to support the SAIs that decide to conduct the audit of development and use of KNI. Such an audit may be seen as a part of the evaluation of efficiency, effectiveness and economy as well as impact and utility of government undertakings, systems, operations, programmes, activities or organisations
Objective of the GUID

## Slide 14
Central concepts for audit of use and development of KNI:
Independence and ethics
SAIs could maintain their independence by providing only technical/expert advice during the development of indicators and not participating in the actual selection of indicators. In particular such advice may contain a relevant set of features used to assess the quality of indicators and/or processes applied (these issues are discussed throughout Part 6 of the GIUD). Alternatively, another way that is widely followed is to not become directly involved during the indicator development phase (but to contribute to it indirectly through audit work) and perform an auditing role after development.
13
34. The auditor shall comply with the SAI’s procedures for independence and ethics, which in turn shall comply with the related ISSAIs on independence and ethics.
35. The auditor shall take care to remain independent so that the audit findings and conclusions are impartial and will be seen as such by the intended users.

## Slide 15
Central concepts for audit of use and development of KNI:
Audit objective(s)
Forms of audit of development and use of KNI:
Prospective evaluation
Ongoing monitoring
Follow-up analysis
12
The main objective of the audit of development and use of KNI is to constructively promote the implementation of evidence based strategic decision-making processes in which relevant and reliable information is available and properly applied throughout the stages. It not only is an important prerequisite of economical, effective and efficient governance, but also contributes to accountability and transparency. Fitness for use and overall quality of performance measurement systems are to be measured against suitable criteria, and the causes of deviations from those criteria or other problems are analysed. Results of the analysis may reveal feasibility of measures taken, as well as assessment of their impacts and associated risks.

## Slide 16
Central concepts for audit of use and development of KNI:
Subject matter
The criteria and corresponding questions are arranged in six broad categories (domains)
Audit of development and use of KNI
Assessment of the KNI system
Evaluation of goals attainment
1. Legal and methodological framework
2. Sufficiency and relevance of indicators set
3. Fitness for use of the indicators set
4. Coherence of the KNI system with other activities
5. Feasibility and soundness of indicators values
6. Adequacy of monitoring and evaluation procedures
14

## Slide 17
Maturity models:
Sufficiency of the indicators set
15
Level 0: No Indicators
Goals attainment is not characterized by indicators or only amount of budgetary resources applied is used
Level 1: Single Indicator
Each goal or policy target is characterized by at least one indicator
Level 2: Multivariate assessment
- Each goal or policy target is characterized by a balanced set of indicators
- All the indicators contain relevant information concerning the goal attainment
- Indicators set contains measures of inputs, outputs and outcomes of goals attainment
Level 3: Inequalities and subjective assessment
- Indicators set provides relevant information about the inequalities in peoples’ well-being in the sphere of programmes and activities implementation
- Indicators set provides relevant information about the subjective assessments of outcomes and impacts
Within each of the categories, the audit or evaluation questions are arranged into a hierarchical structure, a maturity model. To be assessed as having a certain level of maturity in a domain the performance measurement system needs to satisfy all the requirements of this level as well as of all of the lower levels.

## Slide 18
PRESENTATION PLAN
16
Project timeline
Key points of the Exposure draft
Steps to be taken

## Slide 19
 | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  | 
 | 4-10 | 11-17 | 18-24 | 25-31 | 1-7 | 8-14 | 15-21 | 22-28 | 29-5 | 6-12 | 13-19 | 20-26 | 27-2 | 3-9 | 10-16 | 17-23 | 24-30 | 1-7 | 8-14 | 15-21 | 22-28 | 29-4 | 5-11 | 12-18 | 19-25 | 26-1 | 2-8 | 9-15 | 16-22 | 23-29
Comments are collected and posted on www.issai.org |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comments are analysed by the working group |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Considerations and draft Endorsement version to be forwarded to KSC that forwards them to FIPP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FIPP consideration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Translation of the draft Endorsement version |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Amendments to the draft Endorsement version (if any) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WG members correct translation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Approved endorsement version is displayed on www.issai.org |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Approved endorsement version to be forwarded to KSC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final endorsement at INCOSAI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
STEPS TO BE TAKEN
17
September 2019,
XXIII INCOSAI
March 28 – April 19
April 19 – May 10
Not later than
June 1
Draft endorsement version will be disseminated among WG on KNI members
Considerations and draft Endorsement version
to be forwarded to the FIPP Liaison Officer
June 25-28, 2019,
FIPP meeting
August 5, 2019
August 9, 2019

## Slide 20
In accordance with the Due Process for the INTOSAI Framework of Professional Pronouncements the draft guidance would be communicated to the auditors society.
while drafting a guidance a due attention would be given to ensure its alignment with basic concepts and principles outlined in Fundamental principles of public sector auditing (ISSAI 100) and Fundamental principles of performance auditing (ISSAI 300) as well as the other Key INTOSAI pronouncements;
while drafting the guidance the WGKNI would seek advice and expertise of other INTOSAI working group working in adjacent fields such as the Subcommittee on Performance auditing or the INTOSAI Working Group on Programme Evaluation, Expert group on SDGs, and INTOSAI Working Group on Big Data;
? while drafting the guidance the WGKNI would seek technical advice and expertise from the leading international organizations working in the field of measuring progress of societies and peoples well-being such as the UN and the OECD;
? in order to ensure universal applicability the draft guidance is to be tested by the members of WGKNI with different national settings in relevant audit engagements. The exact timing and scope of such audit enagagements are expected to be agreed upon during the 11th meeting of WGKNI in April 2018 in Rome, Italy;
the WGKNI would communicate with INTOSAI committees, in particular with the Knowledge Sharing Committee, the key stages of the guidance development in accordance with the Due Process for the INTOSAI Framework of Professional Pronouncements.
19
Quality assurance procedures to be followed according to project proposal

## Slide 21
Translation into INTOSAI languages
English
French
German
Spanish
Arabic
20

## Slide 22
THANK YOU!