## Slide 1
WORKING GROUP PLAN FOR 2019
Dmitry Zaytsev
Accounts Chamber of the Russian Federation
Bratislava, Slovakia April 2-4, 2019

## Slide 2
2
WORKING GROUP PLAN FOR 2019
№ | Activities | Time | Coordinator
1. | The 12th meeting of the Working Group | April 2-4, 2019 Bratislava (Slovakia) | SAI of Slovakia, Secretariat, WG members

## Slide 3
3
WORKING GROUP PLAN FOR 2019
№ | Activities | Time | Coordinator | 
2. | Guidance on auditing the use and development of key national indicators |  |  | 
2.1 | Releasing the exposure draft of the Guidance on auditing the use and development of key national indicators for public comment on www.issai.org | December 27, 2018 –March 27, 2019 |  | Secretariat
2.2 | Posting on www.issai.org all the comments collected during the exposure period | by April 26, 2019 |  | Secretariat
2.3 | Developing the endorsement version of the Guidance on auditing the use and development of key national indicators | May, 2019 |  | Secretariat, WG members

## Slide 4
4
WORKING GROUP PLAN FOR 2019
№ | Activities | Time |  | Coordinator | 
2. | Guidance on auditing the use and development of key national indicators |  |  |  | 
2.4 | Forwarding the considerations of the working group regarding the received comments to FIPP in a form that is suitable for display on www.issai.org |  | June 25-28, 2019 |  | Secretariat
2.5 | Displaying the approved endorsement version on www.issai.org together with communications on the effective date and the considerations of the working group regarding the comments received through the exposure period as well as the conclusions drawn by FIPP as basis for the approval |  | July, 2019 |  | Secretariat
2.6 | Translation of the approved endorsement version into the five official INTOSAI languages |  | August, 2019 |  | Secretariat, WG members

## Slide 5
7
WORKING GROUP PLAN FOR 2019
№ | Activities | Time |  | Coordinator | 
3. | The 11th KSC Steering Committee Meeting, June 12-14, 2019, Manila, Philippines |  |  |  | 
3.1 | Preparing the report on the Working Group activities 2018-2019 and agreeing it with the WG members |  | May, 2019 |  | Secretariat, WG members
3.2 | Presentation of the report on the Working Group activities 2018-2019 at the 11th KSC Steering Committee Meeting |  | June 12-14, 2019 |  | Secretariat

## Slide 6
8
WORKING GROUP PLAN FOR 2019
№ | Activities | Time |  | Coordinator | 
4. | The 72nd and 73rd INTOSAI Governing Board Meeting, September 23, 29, 2019, Moscow, Russia |  |  |  | 
4.1 | Preparing the report on the Working Group activities 2016-2019 and agreeing it with the WG members |  | October, 2019 |  | Secretariat, WG members
4.2 | Presentation of the report on the Working Group activities for 2016-2019 at the 72nd INTOSAI Governing Board Meeting |  | September 23, 2019 |  | Secretariat

## Slide 7
9
WORKING GROUP PLAN FOR 2019
№ | Activities |  | Time | Coordinator | 
5. | INCOSAI XXIII, September 24-29, 2019, Moscow, Russia |  |  |  | 
5.1 | Presentation of the report on the Working Group activities 2016-2019 | September 24-29, 2019 |  |  | Secretariat

## Slide 8
10
WORKING GROUP PLAN FOR 2019
№ | Activities | Time |  | Coordinator | 
6. | Transformation of the Working group |  |  |  | 
6.1 | Discussion and approval of new goals and the name of the Working group |  | April 2-4, 2019 Bratislava (Slovakia) |  | Secretariat, WG members
6.2 | Developing the draft of the Terms of reference of the Working group |  | April-May, 2019 |  | Secretariat, WG members
6.3 | Submit the Terms of reference of the Working group to INTOSAI Committee on Knowledge Sharing and Knowledge Services for further approval by the INTOSAI Governing Board |  | June, 2019 |  | Secretariat

## Slide 9
11
WORKING GROUP PLAN FOR 2019
№ | Activities | Time | Coordinator
7. | New framework agreement between INTOSAI and OECD | Entire period | Secretariat
8. | Joint work with the discussion group on SDGs headed by the SAI of United Arab Emirates | Entire period | Secretariat
9. | Developing contacts with the UN, the WB and other organizations on the SDG 2030 issues | Entire period | Secretariat, WG members
10. | Developing cooperation with the INTOSAI Working Groups and regional economic organizations | Entire period | Secretariat, WG members
11. | Preparing the 13th meeting of the Working Group on KNI | Entire period | SAI of Belarus, Secretariat, WG members

## Slide 10
THANK YOU!